# HardwareOps (Robotics Wedge)
Initial Tech Stack + Implementation Steps

Version 0.1 • Dylan Frausto • Date: 2026-02-01

# 1. Principles for the v1 Stack

Ship fast, operate simply: minimal moving parts, boring dependencies, easy install in a customer VPC/on‑prem.

Agent must be a single static-ish binary with low runtime friction and good networking primitives.

Control plane must be API-first, testable, and easy to iterate; avoid premature microservices.

Prefer self-hostable components (S3-compatible storage, Postgres) to keep enterprise adoption easy.

# 2. Recommended v1 Tech Stack (Opinionated)

| Decision | Choice + Rationale |
| --- | --- |
| Device Agent | Go (static binary, cross-compile, strong TLS/mTLS, simple concurrency). |
| Control Plane API | Go + Chi/Fiber (fast dev, consistent language with agent) OR Python FastAPI (very fast iteration). For focus and re-use: Go. |
| Database | PostgreSQL (core state + audit logs; easy ops; strong constraints). |
| Queue / Workers | Start DB-backed jobs (Postgres table + SKIP LOCKED) to avoid extra infra; add Redis/NATS later when needed. |
| Artifact Storage | S3-compatible object storage. Use MinIO for on-prem pilots; later support AWS S3/GCS/Azure via S3 API or pluggable backends. |
| Auth / RBAC | JWT for UI/API users + RBAC tables in Postgres. mTLS cert auth for devices. |
| Device Certificates | Small internal CA service (control plane) issuing device certs from enrollment tokens/CSR; rotate later. |
| Web UI | Start with a minimal React/Next.js console or a simple server-rendered UI. For speed: React + Vite + simple pages. |
| CLI | Go CLI using Cobra. Mirrors API calls; supports automation for early design partners. |
| Observability (CP) | Prometheus metrics + structured logs (zap/zerolog) + OpenTelemetry traces (optional initially). |
| Deployment | Docker Compose for pilots; Helm chart for Kubernetes installs once you have 1-2 customers. |

# 3. Repository Layout (Monorepo for v1)

A monorepo keeps iteration speed high early; split later if needed.

repo/

agent/                 # Go device agent (systemd-friendly)

control-plane/         # Go API + worker(s)

ui/                    # Web console (React)

cli/                   # Go CLI

deploy/

compose/             # docker-compose.yaml + env templates

helm/                # (later) Helm chart

docs/                  # architecture + runbooks

proto/ (optional)      # if you later add protobuf schemas

# 4. Key Implementation Choices (v1)

## 4.1 Update Packaging Strategy

Start with artifact bundles: a versioned tar.gz containing binaries/config + a manifest.json (checksums + signature).

Agent downloads bundle, verifies signature + SHA256 checksums, extracts into a versioned directory, and swaps a symlink (atomic).

Rollback is switching the symlink back to prior version + restarting services.

## 4.2 Device Execution Model

Agent runs as a systemd service on the robot host OS.

Agent manages one or more 'managed services' defined in local policy (systemd unit names or container compose).

Remote Actions are allowlisted (restart service, collect logs, run self-test script) with timeouts and output capture.

## 4.3 Rollouts

Rollouts are state machines stored in Postgres; worker progresses stages based on gating thresholds.

Health gates in v1: heartbeat present, last update success, managed services healthy, optional self-test result.

# 5. Implementation Steps (M0 → M3)

## Milestone 0 — Project Setup (1–3 days)

Create monorepo with agent/, control-plane/, ui/, cli/, deploy/compose/, docs/.

Set up CI: lint + unit tests for Go, build agent binaries for linux/amd64 and linux/arm64, build control-plane image.

Define v1 API contract (OpenAPI) for: enroll, check-in, devices, desired-state, rollouts, actions, audit.

## Milestone 1 — Thin Vertical Slice (2–4 weeks)

Control-plane: Postgres schema migrations (golang-migrate), basic device registry tables.

Enrollment v1: create enrollment token in CP → agent first-run uses token to request a device cert (CSR) → CP signs and returns cert.

Agent: implement mTLS check-in loop (heartbeat) and 'current state' report (version/config/health).

Desired state: CP returns desired_version + artifact URL + config revision for device group.

Artifact download: agent downloads bundle (supports resume if possible), verifies SHA256, extracts to /opt/hardwareops/versions/<ver>.

Apply: agent switches /opt/hardwareops/current -> <ver> (symlink) and restarts a single managed service (configurable).

Report: agent posts update result + error codes; CP stores in rollout_events and device_state.

UI (minimal): list devices, view device details (last seen, current/desired, last update result).

## Milestone 2 — Rollouts + Safety (3–6 weeks)

Rollout model: stages (percent/label selector), per-stage success threshold, max failure count, timeout.

Worker: allocate devices to stage (deterministic), set desired_state for those devices, watch results.

Health gating: pause stage on anomaly; expose pause/resume/rollback endpoints.

Rollback: store last_known_good desired version per group; switch desired_state back; agent rollback routine identical to apply.

RBAC v1: roles (admin, deployer, viewer) scoped to fleet; simple JWT auth for UI/CLI.

## Milestone 3 — Git-Native Desired State + Drift (4–8 weeks)

Add Git desired-state option: poll repo or accept webhook; parse fleet/group YAML into desired_state rows.

Validate configs: schema validation (JSONSchema or custom) + dry-run plan output.

Drift detection: agent reports local config hash; CP compares to desired; UI highlights drift and allows reconcile.

Hardening: certificate rotation path, artifact signature enforcement toggle, action allowlist policies.

# 6. Practical Local Dev + Pilot Infra (Docker Compose)

docker-compose: postgres, minio, control-plane (api+worker), ui (optional), reverse proxy (caddy/nginx) for TLS.

Use a self-signed CA for local device certs; ship a dev bootstrap script to create CA + initial admin user.

Include a 'device simulator' binary to emulate N devices checking in for load testing.

# 7. What to Build First (to avoid overbuilding)

Focus the first demo on: enroll → device appears → set desired version → agent updates → report success → rollback works.

Do not build multi-tenant SaaS, advanced telemetry pipelines, or complex policy engines in v1.

Do not build a full UI framework; 5–8 pages is enough for pilots.

# 8. Deliverables Checklist

OpenAPI spec (v1) + generated client for CLI

Go agent v0.1 (enroll, check-in, download/apply/rollback, report)

Control plane v0.1 (device registry, desired state, rollouts, actions, audit)

Compose-based install + quickstart scripts

Pilot runbook + threat model notes

# 9. Next Decisions to Lock In (Before Coding Too Much)

Target device OS baseline (Ubuntu 22.04/24.04) and update mechanism (systemd-managed service vs container).

Artifact type (tar bundle vs container image). Start tar bundle; add container integration later.

Required health gates for robotics design partners (define 2–3 signals that matter).